## Task library
# | title | workstream | task_type | activations | owner | due_amount | due_unit | due_ref | start_amount | start_unit | start_ref | recurrence | notes | Automation tier | Automation approach
1 | Create initial project plan | Project setup & cadence | Internal | All events | Fernando | 3 | months | before event |  |  |  | none | Fern leads creation; hands day-to-day execution to Christina ~1-2 months out. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
2 | Event internal kick-off call | Project setup & cadence | Internal | All events | Fernando + Christina | 3 | months | before event |  |  |  | none | Align full team on project plan, ownership, and timeline. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
3 | Fern → Christina handoff | Project setup & cadence | Internal | All events | Fernando + Christina | 2 | months | before event |  |  |  | none | After kickoff, Fern hands the plan to Christina to run day-to-day. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
4 | Register on-site team for event | Project setup & cadence | Internal | All events | Christina | 1 | months | before event | 2 | months | before event | none | Register all team members. Send confirmations + notify Fern. Dependent on receiving registration link from Informa/event organizer. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
5 | Build internal hub | Project setup & cadence | Internal | All events | Christina | 2 | months | before event |  |  |  | none | Internal attendee tracking (multi-tab Google Sheet). Raw copy-paste from registration site. Distinct from Notion dossier master list. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
6 | Set up Google Script for attendee list propagation | Project setup & cadence | Internal | All events | Christina | 2 | months | before event |  |  |  | none | Set up the Google Script that auto-propagates attendee data into the internal hub. Internal hub is built first. Client EXT list IDs are added later once the EXT list is received — at that point, start the weekly update cadence. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
7 | Internal team reporting — Monday action items | Project setup & cadence | Internal | All events | Christina | 0 | days | on event date | 2 | months | before event | weekly | Monday: send team their action items for the week. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
8 | Internal team reporting — Wednesday mid-week check-in | Project setup & cadence | Internal | All events | Christina | 0 | days | on event date | 2 | months | before event | weekly | Wed/Thu: reminder for anything not yet completed that week. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
9 | Internal team reporting — Friday look-ahead | Project setup & cadence | Internal | All events | Christina | 0 | days | on event date | 2 | months | before event | weekly | Friday: preview of what's coming the following week. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
10 | Internal post-event debrief | Project setup & cadence | Internal | All events | Fernando | 2 | weeks | after event |  |  |  | none | Fern creates a slide deck covering wins, improvements, and key numbers. Full team, 1-hour meeting. Distributed within 48 business hours of the event. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
11 | Project wrap-up + template update | Project setup & cadence | Internal | All events | Fernando + Christina | 2 | weeks | after event |  |  |  | none | Close out the plan, document lessons learned, update templates for next event. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
12 | Client kick-off email | Client comms & calls | Comms | All events | Client partner | 2 | months | before event |  |  |  | none | Sent after signing (Fern or Nic). Event overview + upcoming items. Asks client to add marketing materials, register, book hotels. Prompts scheduling of prep, deal strategy, and debrief calls. Includes key links. Note: Beth may fill client partner role — flag for Fern. Action items for client: register for event and book hotel. Include registration and hotel links if available. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
13 | Collect client to-dos | Client comms & calls | Client | All events | Client partner | 2 | months | before event |  |  |  | none | Collect client to-dos before the client kickoff call — the kickoff is where those to-dos get listed and assigned. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
14 | Send top 20 target request + EXT attendee list | Client comms & calls | Comms | All events | Client partner | 6 | weeks | before event |  |  |  | none | Send the client EXT spreadsheet (initial Informa attendee list). Client marks their top 20 operators to invite to 858 activations. Note: Beth may fill client partner role — flag for Fern. When EXT list is received, update the Google Script with client EXT spreadsheet IDs and start weekly update cadence. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
15 | Create + maintain client external (EXT) spreadsheets | Client comms & calls | Client | All events | Christina | 0 | days | on event date | 6 | weeks | before event | weekly | External Google Sheets with attendee list shared with each client. Refresh weekly as Informa sends updates. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
16 | Remind clients to schedule all three meetings | Client comms & calls | Client | All events | Client partner | 4 | weeks | before event |  |  |  | weekly | Optional. By 4 weeks out, three meetings should be scheduled: prep call (2 weeks before), deal strategy call (1 week before), debrief call (1 week after). Remind weekly if not yet confirmed. Timing depends on overall client communication volume. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
17 | Send dossier live email | Client comms & calls | Comms | All events | Christina + Client partner | 3 | weeks | before event |  |  |  | none | Includes the Rebrandly dossier link + instructions to complete the prioritization exercise (tier 1/2, current customers, detractors). | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
18 | Connect ESM with client (intro) | Client comms & calls | Client | All events | Client partner | 3 | days | before event |  |  |  | none | Intro each client to their ESM via email/text + contact info. ESM ensures client meets and tracks their targets onsite. Note: Beth may fill client partner role — flag for Fern. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
19 | Client prep kickoff call | Client comms & calls | Client | All events | Client partner + Nic | 2 | weeks | before event |  |  |  | none | Walks through the prep deck: logistics, expectations, activation format, Q&A. Note: Beth may fill client partner role — flag for Fern. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
20 | Client deal strategy call | Client comms & calls | Client | All events | JG | 1 | weeks | before event |  |  |  | none | JG on client strategy, goals, and how to approach their tier 1/tier 2 targets. If assigned seating, reviews their table + workshop group for target coverage. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
21 | Post-event client thank you message via text or LinkedIn | Client comms & calls | Comms | All events | JG | 1 | days | after event |  |  |  | none | Quick personal text or LinkedIn thank-you to the client for attending. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
22 | Client debrief call | Client comms & calls | Client | All events | Client partner | 1 | weeks | after event |  |  |  | ongoing | Continues until all client meetings are completed. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
23 | ESM tracks top target intros with clients | Client comms & calls | Client | All events | Client partner + ESMs | 0 | days | on event date |  |  |  | none | ESMs track introductions between clients and their top targets on event day. Ensures each client connects with their key targets. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
24 | ESM introductions, tracking on-site | Client comms & calls | Client | All events | Client partner + ESMs | 0 | days | on event date |  |  |  | none | ESMs use the trackers to ensure each client meets their tier 1/2 targets onsite. All ESMs give simultaneous 5-minute personal warnings for session transitions. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
25 | Add client top 20 targets to internal hub | Invite campaign | Internal | All events | TBD | 6 | weeks | before event |  |  |  | none | Add one tab per client to the internal hub with their top 20 target list based on the top 20 target exercise. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
26 | Invite campaign wave management | Invite campaign | Comms | All events | JG | 6 | weeks | before event | 6 | weeks | before event | weekly | Invite campaign must be planned and set up 6 weeks before the event. Runs weekly through the event — sometimes last-minute invites go out the week of the event. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
27 | Send invites to nominated top targets | Invite campaign | Comms | All events | TBD | 6 | weeks | before event | 6 | weeks | before event | ongoing | 858-specific invite campaign for top 20 nominated targets. Not part of Informa or ICR invite process. Send as needed — ongoing maintenance, not strict weekly cadence. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
28 | Build Notion master attendee list | Client dossiers | Content | All events | Christina | 4 | weeks | before event |  |  |  | none | Enriched master list. Per attendee: full name, job title, brand, LinkedIn, headshot, brand facts (2-3 sentences on education/past roles), buyer intent (own column from registration), registration date + email. Distinct from internal hub. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
29 | Build client dossier attendee list | Client dossiers | Content | All events | Christina | 4 | weeks | before event |  |  |  | none | Per-client attendee list, separate from master. Copy operator info from master minus buyer intent, add buyer-intent column showing ONLY intents matching that client's solution. Never expose other clients' info or non-matching intents. Flag newly added attendees since last refresh. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
30 | Create copy for client dossier | Client dossiers | Content | All events | Christina + Fernando | 4 | weeks | before event |  |  |  | none | Draft all copy for the client dossier page: intro, agenda, team bios, contextual copy. Created before building the dossier page. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
31 | Build client dossier page in Notion | Client dossiers | Content | All events | Christina | 4 | weeks | before event |  |  |  | none | Build full dossier page including: intro, agenda, copy, team bios, maps, priority targets, full attendee list. One Notion page per client. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
32 | QA client dossier | Client dossiers | Content | All events | Christina | 4 | weeks | before event |  |  |  | none | CRITICAL QA before link goes live. Checklist: all links live and working, each client has only their own attendee list (no cross-client data), no spelling errors, all Notion pages published with correct sharing, shareable link confirmed working, client-specific data (buyer intents, GRIP schedule) verified accurate. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
33 | Publish client dossier + attendee list; set share permissions | Client dossiers | Internal | All events | Christina | 4 | weeks | before event |  |  |  | none | Publish both the client dossier page and attendee list in Notion. Set share permissions. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
34 | Create Rebrandly link with clean slug per client dossier | Client dossiers | Internal | All events | Christina | 4 | weeks | before event |  |  |  | none | Copy the Notion share link into Rebrandly. Create a clean, readable slug for each client dossier. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
35 | Run prioritization exercise with clients | Client dossiers | Client | All events | Christina | 3 | weeks | before event |  |  |  | none | Clients complete after receiving dossier live email. Results inform seating chart, room assignments, and ESM trackers. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
36 | Update dossier attendee list | Client dossiers | Content | All events | Christina | 4 | weeks | before event | 4 | weeks | before event | ongoing | Starts when dossier is live. Updated daily or multiple times per week as registrations and cancellations occur. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
37 | Add seating, table assignments, room assignments, and GRIP schedule to dossier | Client dossiers | Content | Luncheon / Workshop / GRIP Meetings | Christina | 1 | weeks | before event |  |  |  | none | Once finalized, add seating and room assignments to the client dossier. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
38 | Final review of dossier attendee list + send updated dossier link | Client dossiers | Internal | All events | Christina | 1 | days | before event |  |  |  | none | Verify the attendee list is as current as possible before doors open. Send updated dossier link to clients if changes were made. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
39 | Book hotels for on-site team | On-site team logistics | Internal | All events | Christina | 4 | weeks | before event |  |  |  | none | Book accommodations for Fern, Christina, and any other on-site team. Per Informa partnership terms where applicable. Info-gathering may happen earlier; actual booking typically ~1 month out. Dependent on receiving hotel link from Informa/event organizer. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
40 | Book team flights | On-site team logistics | Internal | All events | Christina | 6 | weeks | before event |  |  |  | none | Each team member books their own flight. Christina sends reminders and collects flight information from all on-site team members. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
41 | Book team dinner reservations | On-site team logistics | Internal | All events | Fernando | 2 | days | before event |  |  |  | none | Book team dinner for the night before (or night of) the event. Confirm headcount, restaurant, and reservation details. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
42 | Arrange ground transportation + car rental | On-site team logistics | Internal | All events | Fernando | 2 | weeks | before event |  |  |  | none | Confirm car rental, ride share logistics, or airport transportation for on-site team. Especially critical for multi-venue days or late-night events. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
43 | Coordinate on-site shipping + last-minute supply run | On-site team logistics | Internal | All events | Fernando + Christina | 1 | weeks | before event |  |  |  | none | Confirm any shipped items are on track to venue. Identify any last-minute supplies needed (e.g., espresso beans, printed materials, office supplies). Assign who picks them up on-site. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
44 | Send team dress code + what to bring brief | On-site team logistics | Internal | All events | Christina | 3 | days | before event |  |  |  | none | Send to all on-site team: dress code (uniform look), what to bring (badge, materials, chargers, day-of supplies), schedule, and final reminders. Ensures everyone looks cohesive and is prepared. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
45 | Create internal team dossier | On-site team logistics | Internal | All events | Christina | 3 | days | before event |  |  |  | none | Internal-only document for the on-site team. Includes dress code, what to bring, day-of logistics, schedule, and key contacts. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
46 | Set up day-of team communication channel | On-site team logistics | Internal | All events | Fernando | 1 | days | before event |  |  |  | none | Set up and brief the team on the day-of communication channel. Ensure all on-site staff are connected. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
47 | Remind on-site team to submit expenses to Fernando via Expensify | On-site team logistics | Internal | All events | Christina | 1 | weeks | after event |  |  |  | none | Remind all on-site team members to submit their event expenses through Expensify to Fernando. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
48 | Pull prioritization data into prioritization spreadsheet | Seating & room assignments | Event logistics | Luncheon / Workshop | JG | 2 | weeks | before event | 3 | weeks | before event | none | Compile each client's tier 1/2, current customers, detractors from their dossier into one spreadsheet for JG. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
49 | Build table/room assignments | Seating & room assignments | Event logistics | Luncheon / Workshop | JG | 10 | days | before event | 2 | weeks | before event | none | JG uses Claude. Rule: each client table = 1-2 tier 1/2 targets + 1 current customer + 0 detractors. Top targets sit left/right of client; current customer across. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
50 | QA table/room assignments | Seating & room assignments | Internal | Luncheon / Workshop | TBD | 10 | days | before event |  |  |  | none | QA review of all table and room assignments before finalizing. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
51 | Review draft assignments with clients | Seating & room assignments | Event logistics | Luncheon / Workshop | JG | 1 | weeks | before event |  |  |  | none | JG may walk clients through draft assignments on the deal strategy call and adjust on feedback. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
52 | Build ESM trackers | Seating & room assignments | Event logistics | All events | Christina | 3 | days | before event |  |  |  | none | Per client: tier 1/2 targets, whether they share a table/room, gaps, and GRIP schedule overlap. Sent to Nic for onsite ESM use. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
53 | Input check-in data into seating automation tool (onsite) | Seating & room assignments | Event logistics | Luncheon / Workshop | Fernando | 0 | days | on event date |  |  |  | none | Tool ingests prioritization data + check-in list and regenerates the seating plan if threshold hit (~10+ no-shows). JG approves any day-of reassignments. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
54 | Assign seating assignments during event rehearsal | Seating & room assignments | Event logistics | Luncheon / Workshop | Fernando + JG | 1 | days | before event |  |  |  | none | During the venue walkthrough/event rehearsal, physically walk the space to confirm table layout and finalize seating placement. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
55 | Draft program guide content | Program guide | Content | All events | Fernando | 3 | weeks | before event |  |  |  | none | Fern runs first draft through Claude. Sends to JG + Marty for review and visual direction. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
56 | JG + Marty review program guide content | Program guide | Internal | All events | JG + Marty | 2 | weeks | before event |  |  |  | none | JG and Marty review and approve content draft. Send approval to Christina to begin Figma build. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
57 | Build program guide in Figma | Program guide | Content | All events | Christina | 2 | weeks | before event |  |  |  | none | Christina builds from template. Includes team, attendees + headshots, maps, guest-speaker spotlights, what to expect. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
58 | Review cycle — JG + Marty review program guide | Program guide | Internal | All events | JG + Marty + Christina | 1 | weeks | before event |  |  |  | none | JG and Marty review the built guide. Christina makes edits. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
59 | QA program guide before PDF export | Program guide | Internal | All events | Christina + JG | 5 | days | before event |  |  |  | none | QA checklist: all headshots correct, all names spelled correctly, all links working, URL slug correct, no incorrect client cross-references, event dates and venue correct. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
60 | Export program guide PDF + convert to shareable link | Program guide | Content | All events | Christina + JG | 5 | days | before event |  |  |  | none | Christina exports PDF after QA sign-off. JG converts to shareable link (Bitly or similar). Link goes into the KBYG email. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
61 | QA know before you go email copy | Program guide | Comms | All events | Christina | 4 | days | before event |  |  |  | none | CRITICAL QA: correct program guide link per client (no cross-client link mixing), all headshots render, email renders across Gmail/Outlook/Apple Mail. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
62 | Send know before you go email | Program guide | Comms | All events | TBD + JG | 3 | days | before event |  |  |  | none | Carries the program guide PDF shareable link. Sent to all operators + clients. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
63 | Confirm floor plan + capacity from venue/Informa | Vendors & logistics | Event logistics | Luncheon / Workshop / 858 House | Fernando | 6 | weeks | before event |  |  |  | none | Confirm floor capacity, table count, room setup with venue or Informa. Needed even when seating isn't assigned. Send floor plan and capacity numbers to JG — needed for seating planning and to size the invite campaign. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
64 | Menu preapproval in writing | Vendors & logistics | Vendors | Luncheon / 858 House / Evening networking | Fernando | 8 | weeks | before event |  |  |  | none | Menu reviewed and approved in writing BEFORE venue contract is signed. Espresso required at every daytime 858 event — non-negotiable. Evening social menu also requires approval. Optional. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
65 | Food + beverage + espresso cart coordination | Vendors & logistics | Vendors | All events | Fernando | 6 | weeks | before event |  |  |  | none | Confirm F&B menu, catering vendor, espresso cart vendor and logistics. Source espresso beans from a client if possible. For 858 House: 9am-4pm snacks, 4pm-7pm cocktails. Lock contracts and confirm delivery times. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
66 | Furniture rental order | Vendors & logistics | Vendors | Luncheon / Workshop / 858 House | Fernando | 6 | weeks | before event |  |  |  | none | Only if bringing furniture from outside the venue. Lock early — often has the earliest vendor deadline. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
67 | Collect tech stand requirements + send to client | Vendors & logistics | Event logistics | Presentation | Christina | 4 | weeks | before event |  |  |  | none | Collect all technical requirements for the tech stand and send to the client. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
68 | JG sends design requests to Fernando + Christina | Vendors & logistics | Internal | Luncheon / Workshop / 858 House / Presentation | JG | 3 | weeks | before event |  |  |  | none | JG sends design briefs and content for signage, badges, and collateral. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
69 | Design signage + badges | Vendors & logistics | Content | Luncheon / Workshop / 858 House / Presentation | Christina | 2 | weeks | before event | 3 | weeks | before event | none | Christina designs badges, note cards, directional signs, table number signs, and collateral. Fern approves and orders printing. Table number signs must be included in photographer's table shot brief. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
70 | Order + ship marketing collateral | Vendors & logistics | Vendors | Luncheon / Workshop / 858 House / Presentation | Fernando | 1 | weeks | before event |  |  |  | none | Order all printed/physical marketing collateral and ship to venue. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
71 | On-site team picks up marketing collateral | Vendors & logistics | Event logistics | Luncheon / Workshop / 858 House / Presentation | On-site team | 1 | days | before event |  |  |  | none | Confirm on-site pickup of all marketing collateral at the venue. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
72 | Swag order | Vendors & logistics | Vendors | All events | Fernando | 4 | weeks | before event |  |  |  | none | Source, brand, and deliver attendee swag to the venue. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
73 | Marketing materials for Informa submission | Vendors & logistics | Content | All events | Christina | 3 | weeks | before event |  |  |  | none | Collect client logos + bios and 858 logo/bio. Submit to event or Informa per required deadlines. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
74 | Confirm AV + tech setup | Vendors & logistics | Event logistics | Luncheon / Workshop / 858 House / Presentation | Fernando | 3 | weeks | before event |  |  |  | none | 858 owns: laptop, HDMI, cables. Purchase and test before event. Never rely on JG's personal equipment or venue Bluetooth. Confirm microphone/PA for any session with 10+ attendees. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
75 | Confirm Wi-Fi + internet access | Vendors & logistics | Event logistics | Luncheon / Workshop / 858 House / Presentation | Fernando | 3 | weeks | before event |  |  |  | none | Confirm venue WiFi credentials and bandwidth for the day. Especially critical for 858 House lounge and any session using live data or real-time tools. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
76 | Hire extra staff | Vendors & logistics | Vendors | Luncheon / Workshop / 858 House | Fernando | 3 | weeks | before event |  |  |  | none | Check-in help, room flips, extra F&B staff as needed. For large-scale events. ESM and brand connector roles evaluated for consolidation. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
77 | Designate music lead + build playlists | Vendors & logistics | Event logistics | 858 House | Fernando | 5 | days | before event |  |  |  | none | Assign music lead (owns the board all day — not a playlist on shuffle). Build moment-by-moment playlists: arrival/registration (warm, low BPM), session opens (fade to zero — 8-second rule), breaks (energy lift), networking, close. Download offline — no streaming dependency. 858-owned equipment (Sonos portable or JBL EON). | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
78 | Vendor parking + load-in/load-out coordination | Vendors & logistics | Vendors | All events | Fernando | 1 | weeks | before event |  |  |  | none | Confirm load-in times, dock access, vendor parking, and load-out schedule for all vendors (espresso, furniture, decor, staffing). | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
79 | Shipping logistics | Vendors & logistics | Vendors | All events | Fernando + Christina | 2 | weeks | before event |  |  |  | none | Coordinate shipping of swag, signage, badges, and any event materials to the venue. Confirm tracking and delivery confirmation. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
80 | Build run-of-show + designate transition leads | Vendors & logistics | Content | All events | Fernando + Christina | 1 | weeks | before event | 2 | weeks | before event | none | Detailed minute-by-minute schedule. Include: where to be and when, designated transition lead per room (JG is NEVER the transition lead), ESM 5-minute warning protocol, and music cues. Also feeds the photography dossier. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
81 | Venue walkthrough + event rehearsal | Vendors & logistics | Event logistics | All events | Fernando | 1 | days | before event |  |  |  | none | Physical walkthrough of ALL venues (day + evening). Fern walks everyone through the space. JG practices speeches. AV setups tested. Music tested. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
82 | Vendor invoice tracking + payment | Vendors & logistics | Vendors | All events | Christina | 2 | weeks | after event | 1 | weeks | after event | none | Track all outstanding vendor invoices post-event. Flag any that are overdue. Notify Fern to process payments per contract terms. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
83 | Create standard copy for handwritten note | Handwritten notes | Internal | Luncheon / Workshop | Christina + JG | 4 | weeks | before event |  |  |  | none | Standard copy for attendees added too late for personalization or not prioritized by JG. Draft before starting spreadsheet. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
84 | Create handwritten notes spreadsheet | Handwritten notes | Internal | Luncheon / Workshop | Christina | 4 | weeks | before event |  |  |  | ongoing | List all attendees including clients. Categorize by note type. Ongoing — update as registrations and cancellations come in. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
85 | Send handwritten notes spreadsheet to JG | Handwritten notes | Internal | Luncheon / Workshop | Christina | 4 | weeks | before event |  |  |  | none | JG reviews and adds personalized note copy for key attendees. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
86 | Update handwritten notes spreadsheet | Handwritten notes | Internal | Luncheon / Workshop | Christina | 4 | weeks | before event | 4 | weeks | before event | ongoing | Ongoing updates as new registrants are added and cancellations occur. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
87 | Produce handwritten notes (run machine) | Handwritten notes | Internal | Luncheon / Workshop | Christina | 2 | weeks | before event |  |  |  | ongoing | Upload finalized spreadsheet to machine software. Run machine to produce notes and envelopes. Repeat as spreadsheet updates. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
88 | QA handwritten notes + envelopes | Handwritten notes | Internal | Luncheon / Workshop | Christina | 1 | weeks | before event |  |  |  | none | Verify all notes are for confirmed attendees. Remove any canceled. Check all envelopes are correctly addressed. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
89 | Package + ship handwritten notes to venue/hotel | Handwritten notes | Event logistics | Luncheon / Workshop | Christina | 1 | weeks | before event |  |  |  | none | Ship via UPS to venue, hotel, or Fernando. Include extra blank cards, envelopes, and the machine pen for on-site additions. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
90 | On-site team picks up handwritten notes package | Handwritten notes | Event logistics | Luncheon / Workshop | On-site team | 1 | days | before event |  |  |  | none | Confirm receipt of the handwritten notes package on-site. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
91 | Write handwritten notes for on-site new additions | Handwritten notes | Internal | Luncheon / Workshop | Christina | 1 | days | before event |  |  |  | none | Write notes for attendees who registered after the shipment was sent. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
92 | Confirm handwritten notes against final attendee list | Handwritten notes | Internal | Luncheon / Workshop | Christina | 1 | days | before event |  |  |  | none | Night before: final match of notes against most current attendee list. Remove notes for cancellations. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
93 | Place handwritten notes on seats/tables | Handwritten notes | Event logistics | Luncheon / Workshop | On-site team | 0 | days | on event date |  |  |  | none | Place each note on the corresponding seat before doors open. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
94 | Set up Luma event page | Activation operations | Event logistics | Luncheon / Workshop / 858 House | Fernando | 6 | weeks | before event |  |  |  | none | Luma event page must be live before invite campaign begins. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
95 | Monitor registration for daily Luma approval | Activation operations | Event logistics | Luncheon / Workshop / 858 House | Christina | 4 | weeks | before event | 4 | weeks | before event | ongoing | Review and approve new registrations in Luma daily. Starts when dossier goes live. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
96 | Send Luma reminder — day before + morning of event | Activation operations | Comms | Luncheon / Workshop / 858 House | Christina | 1 | days | before event |  |  |  | none | Send Luma reminder email the day before. Send again morning of event with location, start time, and check-in instructions. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
97 | Brief chief of staff | Activation operations | Internal | Luncheon / Workshop | Fernando | 1 | days | before event |  |  |  | none | Brief Fern or designee on the day's plan. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
98 | Day-of check-in setup + live no-show tracking | Activation operations | Event logistics | Luncheon / Workshop | On-site team | 0 | days | on event date |  |  |  | none | Set up check-in (iPad/list, registration desk, escort). Capture walk-ins. Track no-shows in real time. Share final check-in list with Nic, JG, and Robin post-event. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
99 | Collect + send group insights post-activation | Activation operations | Internal | Luncheon / Workshop | Client partner + ESMs | 1 | days | after event |  |  |  | none | Collect Granola recording, note card takeaways, and key themes from each workshop room. Send summary to the team. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
100 | Recruit + confirm workshop moderators | Activation operations | Event logistics | Workshop | Fernando + JG | 4 | weeks | before event |  |  |  | none | Identify and confirm one moderator per room. 4 rooms = 4 moderators. Confirm availability on the content planning call. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
101 | Build workshop discussion prompts + content framework | Activation operations | Content | Workshop | JG | 4 | weeks | before event |  |  |  | none | Pre-set discussion questions, ranking exercises, group discussion format per table/room. Each sub-group nominates one person to share back. Questions approved by 858 in advance. Moderators need clear questions + expected outcomes. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
102 | Write moderator guide | Activation operations | Content | Workshop | JG | 3 | weeks | before event |  |  |  | none | Create one-page moderator guide per room: session objectives, discussion questions, timing, ground rules, what to do if conversation stalls. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
103 | Schedule + prepare moderator prep meeting | Activation operations | Internal | Workshop | JG | 2 | weeks | before event |  |  |  | none | Schedule and prepare all materials for the moderator prep meeting. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
104 | Hold moderator prep meeting + distribute notes | Activation operations | Internal | Workshop | JG | 2 | weeks | before event |  |  |  | none | Brief all moderators before event day. Distribute meeting notes and cheat sheet for each room. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
105 | Prep workshop room supplies + Granola setup | Activation operations | Event logistics | Workshop | Fernando + Christina | 1 | days | before event |  |  |  | none | Note cards, pens, name tents per seat, printed discussion prompts at each table. Set up Granola recording device in each room. Confirm furniture and room layout match the floor plan. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
106 | Write + approve sponsor intro scripts | Activation operations | Content | Luncheon | Fernando + JG | 1 | weeks | before event |  |  |  | none | JG delivers ALL sponsor introductions (30-second scripted reads). Format: operator problem first, one differentiating line, named customer in the room, named sponsor rep. Sponsors NEVER self-present. Scripts locked by 858 in advance. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
107 | Build + confirm housekeeping slides with client logos | Activation operations | Content | Luncheon | Fernando | 2 | weeks | before event |  |  |  | none | Slides shown during remarks with client logos rotating on screen. Confirm screen/monitor availability with venue contact. Confidence monitor also confirmed. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
108 | Write + finalize JG opening remarks | Activation operations | Content | Luncheon / Workshop / Presentation | JG | 1 | weeks | before event |  |  |  | none | JG drafts opening remarks. Include: how clients are introduced (operator problem first — never self-presented), event framing, and client intro remarks. Multiple review rounds before final. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
109 | 858 House venue + lounge setup coordination | Activation operations | Event logistics | 858 House | Fernando | 4 | weeks | before event |  |  |  | none | Luxury lounge feel. Full bar, espresso, high-end F&B. Confirm room setup, furniture, and vendor logistics. Confirm lounge hours. Determine if tent needed. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
110 | 858 House check-in + table reservations setup | Activation operations | Event logistics | 858 House | Fernando | 1 | weeks | before event |  |  |  | none | Build check-in system. Clients can reserve tables in advance for prospect meetings. Confirm escort and front-desk check-in staffing. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
111 | Confirm GRIP designate per partner | Activation operations | Event logistics | GRIP Meetings | Client partner | 4 | weeks | before event | 6 | weeks | before event | none | Each partner assigns one person (designator) to log into GRIP and make selections for the company. Each client gets 10 meetings per company even with 2 attendees. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
112 | Client completes GRIP operator preference selections (top 40) | Activation operations | Event logistics | GRIP Meetings | Client partner | 3 | weeks | before event | 4 | weeks | before event | none | Designator logs into GRIP and selects up to 40 operators to meet. Cross-reference dossier tier 1/2 to help prioritize. Operators also make selections; GRIP matches on mutual interest. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
113 | Review preliminary GRIP meeting schedule + flag issues | Activation operations | Event logistics | GRIP Meetings | Client partner | 1 | weeks | before event |  |  |  | none | Informa publishes a draft schedule. Review each client's 10 meetings and flag conflicts or mismatches directly with Informa. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
114 | GRIP on-site support + ESM coverage | Activation operations | Event logistics | GRIP Meetings | Client partner + ESMs | 0 | days | on event date |  |  |  | none | 10 x 10-min back-to-back 1:1s per client. ESMs keep each client on time and equipped, flag no-shows, manage transitions between meetings. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
115 | Presentation: submit materials to Informa | Activation operations | Content | Presentation | Fernando + JG | 2 | weeks | before event |  |  |  | none | Submit presentation deck, speaker bio/headshot, and any supporting materials required by Informa. Confirm submission deadlines with Informa contact. For CREATE: submit Innovation Forum materials per Informa deadline. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
116 | Presentation: AV rehearsal + final speaker prep | Activation operations | Content | Presentation | JG + Fernando | 1 | days | before event |  |  |  | none | JG rehearses the presentation. Test AV, clicker, slide transitions. Confirm confidence monitor. Happens during the venue walkthrough day before. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
117 | Research + identify guest speaker candidates | Activation operations | Event logistics | Guest speaker | JG + Fernando | 8 | weeks | before event |  |  |  | none | JG, Fernando, and Marty identify who they want as outside speaker or guest draw. Fit criteria: relevant to operator audience, credible brand, willing to participate. Build shortlist. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
118 | Outreach to guest speaker candidates | Activation operations | Event logistics | Guest speaker | Fernando | 6 | weeks | before event |  |  |  | none | Fern leads outreach to speaker candidates. Confirm interest, availability, format, and any fee or reimbursement expectations. Escalate to JG for any high-profile targets. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
119 | Confirm + sign guest speaker agreement | Activation operations | Event logistics | Guest speaker | Fernando | 5 | weeks | before event |  |  |  | none | Sign agreement covering format, session length, travel/hotel reimbursement policy, invoice process, and any usage rights. Confirm speaker is aware this is not a self-promotional slot. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
120 | Guest speaker briefing meeting | Activation operations | Event logistics | Guest speaker | Fernando + Christina | 3 | weeks | before event |  |  |  | none | Meet with confirmed speaker to walk through: 858 event format, what their session looks like, how long, who the audience is, what we expect (not a sales pitch), what to expect from attendees, Q&A format. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
121 | Collect speaker bio + headshot | Activation operations | Event logistics | Guest speaker | Christina | 1 | weeks | before event |  |  |  | none | Collect speaker's bio, headshot, and preferred contact info. Used in: program guide (speaker spotlight section), post-event recap (guest speaker section), and post-event comms. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
122 | Send speaker run-of-show, collateral + logistics brief | Activation operations | Event logistics | Guest speaker | Fernando + Christina | 1 | weeks | before event |  |  |  | none | Send speaker the run-of-show, all event collateral, and full logistics brief: on-site contact, arrival logistics, hotel booking details. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
123 | Coordinate speaker travel + hotel invoice reimbursement | Activation operations | Event logistics | Guest speaker | Fernando | 2 | weeks | after event |  |  |  | none | Speaker books their own travel and hotel. After the event, collect invoice(s) and process reimbursement per agreement terms. Confirm with Fern on payment timeline. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
124 | Research + vet photographers | Photography | Vendors | All events | Christina | 8 | weeks | before event |  |  |  | none | Get 2-3 quotes per city. Review portfolios. Research walk-in headshot options for unregistered attendees. Consider past photographers by city. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
125 | Negotiate + sign photography contract | Photography | Vendors | All events | Christina | 6 | weeks | before event |  |  |  | none | Contract MUST include: same-day selects (20-40 edited photos by EOD or early next morning), 24-48 hr full gallery delivery SLA with rush fee pre-approved. Pre-event call if first time with 858. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
126 | Pay photography deposit | Photography | Vendors | All events | Fernando + Christina | 6 | weeks | before event |  |  |  | none | Pay deposit per contract terms immediately upon signing. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
127 | Build photographer dossier + Robin dossier | Photography | Vendors | All events | Christina | 1 | weeks | before event |  |  |  | none | Build photographer's and Robin's dossiers. Includes run-of-show, event schedule, key shot list, contacts. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
128 | Send photographer dossier + Robin dossier (with updated attendee list) | Photography | Vendors | All events | Christina | 3 | days | before event |  |  |  | none | Send finalized dossiers to photographer and Robin with the most current attendee list. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
129 | Receive same-day photo selects | Photography | Vendors | All events | Christina | 0 | days | on event date |  |  |  | none | Receive 20-40 edited photos from photographer by EOD or early next morning. Must include all table/room linking shots. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
130 | Organize same-day photo selects by table/room + send to TBD | Photography | Vendors | Luncheon / Workshop | Christina | 1 | days | after event |  |  |  | none | Organize same-day selects by table or room. Send organized folder to TBD for table/room linking emails. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
131 | Receive full photo gallery from photographer | Photography | Vendors | All events | Christina | 3 | days | after event |  |  |  | none | Per contract SLA (3-7 business days). 200-1,000 photos: speakers, food/decor, venue, candids, team, all linking shots. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
132 | Send gallery + final check-in list to Robin | Photography | Vendors | All events | Christina | 7 | days | after event |  |  |  | none | Include full gallery, final check-in list with no-shows flagged, and updated attendee list (including any walk-in headshots researched) for Robin's reference when organizing. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
133 | Robin organizes photos by operator + delivers folders | Photography | Vendors | All events | Christina | 10 | days | after event | 7 | days | after event | none | Robin creates one folder per operator (50-200+ people). Takes approximately 2-4 business days. Christina confirms delivery and quality. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
134 | Approve Robin invoice + notify Fern for payment | Photography | Vendors | All events | Christina | 10 | days | after event |  |  |  | none | Christina approves Robin's invoice, then notifies Fern to process payment via Gusto. Robin paid $450/event for photo organization. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
135 | Pay photographer final invoice | Photography | Vendors | All events | Fernando + Christina | 2 | weeks | after event |  |  |  | none | Process photographer's final payment per contract terms after gallery delivery confirmed. | Tier 3 | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
136 | Create email copy doc for linking emails | Table & room linking emails | Comms | Luncheon / Workshop | Christina | 1 | weeks | before event |  |  |  | none | Open doc pre-event; stage with placeholder table structure, LinkedIn link slots, and photo placeholders so JG can preview the format before event day. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
137 | JG edits + approves email copy for linking emails | Table & room linking emails | Comms | Luncheon / Workshop | JG | 5 | days | before event |  |  |  | none | JG reviews and approves linking email copy before staging. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
138 | Stage mock linking email for JG approval | Table & room linking emails | Comms | Luncheon / Workshop | TBD | 4 | days | before event |  |  |  | none | TBD stages a mock email. JG reviews and approves. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
139 | Receive same-day photo selects + organize by table/room | Table & room linking emails | Comms | Luncheon / Workshop | Christina | 1 | days | after event |  |  |  | none | Same-day selects must include all table and room linking shots. Christina labels and drops linking shots into Google Drive folders organized by table/room. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
140 | Receive check-in list | Table & room linking emails | Comms | Luncheon / Workshop | Christina | 1 | days | after event |  |  |  | none | Receive from on-site team. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
141 | Send TBD the Google folders (organized photos, check-in list, Notion dossier for LinkedIns) | Table & room linking emails | Comms | Luncheon / Workshop | Christina | 1 | days | after event |  |  |  | none | Send TBD: organized operator photo folders, final check-in list, Notion dossier links for LinkedIn lookups. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
142 | Finalize email distribution list organized by table/room | Table & room linking emails | Comms | Luncheon / Workshop | TBD | 1 | days | after event |  |  |  | none | TBD organizes final confirmed seating — removes no-shows, adds walk-ins, confirms accurate table/room mapping. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
143 | Populate linking emails: photos + LinkedIn + table discussion note | Table & room linking emails | Comms | Luncheon / Workshop | TBD | 1 | days | after event |  |  |  | none | Insert final table/room photos + LinkedIn profile links per attendee + a brief note on what the table discussed. One email per table (luncheon) or room (workshop). | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
144 | QA all linking emails before send | Table & room linking emails | Comms | Luncheon / Workshop | TBD | 1 | days | after event |  |  |  | none | CRITICAL QA: each email contains ONLY that table's photos and links (no cross-client mixing), all LinkedIn URLs valid, all photos render, no-shows removed, copy sounds personal not AI-generated. Test email across Gmail/Outlook/Apple Mail. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
145 | Final review + send linking emails | Table & room linking emails | Comms | Luncheon / Workshop | TBD + JG | 2 | days | after event |  |  |  | none | JG final review and approval. Send individually — one email per table (luncheon) or room (workshop). | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
146 | Collect brand + client feedback, Granola notes + chief of staff notes | Post-event recap | Comms | All events | Christina + Nic | 3 | days | after event |  |  |  | none | Collect all post-event input: brand feedback, client feedback, Granola meeting notes, and chief of staff notes. Feeds into recap copy draft. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
147 | Draft post-event recap copy | Post-event recap | Comms | All events | Christina | 3 | days | after event |  |  |  | none | Full recap structure: intro, event overview, carousel of highlights, reporting/infographic (Nic), guest speaker spotlight, brand exec quotes (operator quotes — no names), feedback and learnings, gratitude (client logos), client attendee headshots + LinkedIn links, event photo album link. Uses program guide, emails, event notes. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
148 | Draft recap video copy | Post-event recap | Comms | All events | Christina | 1 | weeks | after event |  |  |  | none | Draft copy for recap video. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
149 | Nic adds reporting layer + infographic | Post-event recap | Comms | All events | Nic | 1 | weeks | after event |  |  |  | none | Buyer-intent reporting, operator/client feedback summary, ESM debrief notes, and infographic visual. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
150 | Nic reviews post-event recap copy (first draft), edits + approves | Post-event recap | Comms | All events | Nic | 1 | weeks | after event |  |  |  | none | Nic reviews Christina's first draft, makes edits, approves, and sends to JG + Marty. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
151 | JG + Marty final content review + approve | Post-event recap | Comms | All events | JG + Marty | 10 | days | after event |  |  |  | none | Final content edit + approval before Webflow build. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
152 | Build visual recap in Webflow | Post-event recap | Comms | All events | Christina | 10 | days | after event |  |  |  | none | Once full gallery is available. Christina builds from Webflow template: photos, infographic, CMS page content, and photo album link all in one combined build. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
153 | Review cycle — JG + Marty review visual recap | Post-event recap | Comms | All events | JG + Marty + Christina | 10 | days | after event |  |  |  | none | JG and Marty review the built visual recap. Christina makes edits. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
154 | QA recap before going live | Post-event recap | Comms | All events | Christina | 12 | days | after event |  |  |  | none | QA checklist: all photo links work, all headshots correct, all names correct, event album link works, Webflow page renders correctly on mobile and desktop, no broken images. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
155 | Make recap live + share link with TBD | Post-event recap | Comms | All events | Christina | 2 | weeks | after event |  |  |  | none | Make the Webflow link live. Share with TBD for inclusion in 1:1 follow-up emails. Share with the broader team. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
156 | Christina sends TBD organized operator photo folders | 1:1 operator follow-up | Comms | All events | Christina | 1 | days | after event |  |  |  | none | Send TBD the Google Drive folders with Robin's organized operator photos for 1:1 emails. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
157 | Create 1:1 follow-up copy doc + template | 1:1 operator follow-up | Comms | All events | Christina + TBD | 1 | weeks | after event |  |  |  | none | Christina creates structure + optional Claude template. TBD and JG own the copy. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
158 | Edit 1:1 email copy doc + template; review + approve | 1:1 operator follow-up | Comms | All events | TBD + JG | 10 | days | after event |  |  |  | none | Personalized per operator — references the event + a personal note from JG. TBD drafts; JG reviews. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
159 | Stage 1:1 emails | 1:1 operator follow-up | Comms | All events | TBD + JG | 10 | days | after event |  |  |  | none | Stage all 1:1 operator emails for final QA and send. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
160 | Attach organized photo from Robin's folders | 1:1 operator follow-up | Comms | All events | TBD | 10 | days | after event |  |  |  | none | TBD pulls each operator's individual photo from Robin's organized folders for individual email attachment. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
161 | QA 1:1 emails before send | 1:1 operator follow-up | Comms | All events | TBD | 10 | days | after event |  |  |  | none | Verify: correct photo per operator, recap link is correct and live, no duplicate sends, copy is personalized not generic, all names spelled correctly. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
162 | Send 1:1 emails individually | 1:1 operator follow-up | Comms | All events | TBD + JG | 10 | days | after event |  |  |  | none | TBD confirms photos + copy per operator. Sends individually — each with their personal photo + the live recap link. JG reviews selectively. | Tier 1 | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
163 | Invited but non-attendee follow-up email | 1:1 operator follow-up | Comms | All events | TBD + JG | 3 | weeks | after event |  |  |  | none | OPTIONAL / conditional. Send a personalized follow-up to people who were invited but did not attend — including no-shows, cancellations, and anyone who never registered. Copy acknowledges they missed it, shares a link to the recap, and keeps the relationship warm. Decide per event whether to run this. | Tier 2 | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.

## Automation tiers
Automation tier | Task | Workstream | Owner | Recurrence | How it gets automated
Tier 1 | Attach organized photo from Robin's folders | 1:1 operator follow-up | TBD | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Christina sends TBD organized operator photo folders | 1:1 operator follow-up | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send 1:1 emails individually | 1:1 operator follow-up | TBD + JG | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Stage 1:1 emails | 1:1 operator follow-up | TBD + JG | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Collect speaker bio + headshot | Activation operations | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Monitor registration for daily Luma approval | Activation operations | Christina | ongoing | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Presentation: submit materials to Informa | Activation operations | Fernando + JG | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send Luma reminder — day before + morning of event | Activation operations | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send speaker run-of-show, collateral + logistics brief | Activation operations | Fernando + Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Set up Luma event page | Activation operations | Fernando | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Create + maintain client external (EXT) spreadsheets | Client comms & calls | Christina | weekly | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Remind clients to schedule all three meetings | Client comms & calls | Client partner | weekly | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send dossier live email | Client comms & calls | Christina + Client partner | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Add seating, table assignments, room assignments, and GRIP schedule to dossier | Client dossiers | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Build Notion master attendee list | Client dossiers | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Build client dossier attendee list | Client dossiers | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Create Rebrandly link with clean slug per client dossier | Client dossiers | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Publish client dossier + attendee list; set share permissions | Client dossiers | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Update dossier attendee list | Client dossiers | Christina | ongoing | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Confirm handwritten notes against final attendee list | Handwritten notes | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Create handwritten notes spreadsheet | Handwritten notes | Christina | ongoing | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send handwritten notes spreadsheet to JG | Handwritten notes | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Update handwritten notes spreadsheet | Handwritten notes | Christina | ongoing | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Add client top 20 targets to internal hub | Invite campaign | TBD | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Invite campaign wave management | Invite campaign | JG | weekly | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send invites to nominated top targets | Invite campaign | TBD | ongoing | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Remind on-site team to submit expenses to Fernando via Expensify | On-site team logistics | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send team dress code + what to bring brief | On-site team logistics | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Set up day-of team communication channel | On-site team logistics | Fernando | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Organize same-day photo selects by table/room + send to TBD | Photography | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Receive full photo gallery from photographer | Photography | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Receive same-day photo selects | Photography | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send gallery + final check-in list to Robin | Photography | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send photographer dossier + Robin dossier (with updated attendee list) | Photography | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Collect brand + client feedback, Granola notes + chief of staff notes | Post-event recap | Christina + Nic | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Make recap live + share link with TBD | Post-event recap | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Export program guide PDF + convert to shareable link | Program guide | Christina + JG | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send know before you go email | Program guide | TBD + JG | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Build internal hub | Project setup & cadence | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Internal team reporting — Friday look-ahead | Project setup & cadence | Christina | weekly | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Internal team reporting — Monday action items | Project setup & cadence | Christina | weekly | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Internal team reporting — Wednesday mid-week check-in | Project setup & cadence | Christina | weekly | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Register on-site team for event | Project setup & cadence | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Set up Google Script for attendee list propagation | Project setup & cadence | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Build ESM trackers | Seating & room assignments | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Pull prioritization data into prioritization spreadsheet | Seating & room assignments | JG | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Finalize email distribution list organized by table/room | Table & room linking emails | TBD | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Populate linking emails: photos + LinkedIn + table discussion note | Table & room linking emails | TBD | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Receive check-in list | Table & room linking emails | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Receive same-day photo selects + organize by table/room | Table & room linking emails | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 1 | Send TBD the Google folders (organized photos, check-in list, Notion dossier for LinkedIns) | Table & room linking emails | Christina | none | Fully automatable — agent runs after a trigger (data move, monitor, templated send, scheduled report, or publish). No human touch.
Tier 2 | Create 1:1 follow-up copy doc + template | 1:1 operator follow-up | Christina + TBD | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Edit 1:1 email copy doc + template; review + approve | 1:1 operator follow-up | TBD + JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Invited but non-attendee follow-up email | 1:1 operator follow-up | TBD + JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | QA 1:1 emails before send | 1:1 operator follow-up | TBD | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Build + confirm housekeeping slides with client logos | Activation operations | Fernando | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Build workshop discussion prompts + content framework | Activation operations | JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Collect + send group insights post-activation | Activation operations | Client partner + ESMs | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Research + identify guest speaker candidates | Activation operations | JG + Fernando | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Review preliminary GRIP meeting schedule + flag issues | Activation operations | Client partner | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Schedule + prepare moderator prep meeting | Activation operations | JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Write + approve sponsor intro scripts | Activation operations | Fernando + JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Write + finalize JG opening remarks | Activation operations | JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Write moderator guide | Activation operations | JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Client kick-off email | Client comms & calls | Client partner | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Send top 20 target request + EXT attendee list | Client comms & calls | Client partner | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Build client dossier page in Notion | Client dossiers | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Create copy for client dossier | Client dossiers | Christina + Fernando | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Final review of dossier attendee list + send updated dossier link | Client dossiers | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | QA client dossier | Client dossiers | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Create standard copy for handwritten note | Handwritten notes | Christina + JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Create internal team dossier | On-site team logistics | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Build photographer dossier + Robin dossier | Photography | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Research + vet photographers | Photography | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Build visual recap in Webflow | Post-event recap | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Draft post-event recap copy | Post-event recap | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Draft recap video copy | Post-event recap | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | JG + Marty final content review + approve | Post-event recap | JG + Marty | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Nic adds reporting layer + infographic | Post-event recap | Nic | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Nic reviews post-event recap copy (first draft), edits + approves | Post-event recap | Nic | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | QA recap before going live | Post-event recap | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Review cycle — JG + Marty review visual recap | Post-event recap | JG + Marty + Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Build program guide in Figma | Program guide | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Draft program guide content | Program guide | Fernando | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | JG + Marty review program guide content | Program guide | JG + Marty | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | QA know before you go email copy | Program guide | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | QA program guide before PDF export | Program guide | Christina + JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Review cycle — JG + Marty review program guide | Program guide | JG + Marty + Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Create initial project plan | Project setup & cadence | Fernando | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Project wrap-up + template update | Project setup & cadence | Fernando + Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Build table/room assignments | Seating & room assignments | JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | QA table/room assignments | Seating & room assignments | TBD | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Create email copy doc for linking emails | Table & room linking emails | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Final review + send linking emails | Table & room linking emails | TBD + JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | JG edits + approves email copy for linking emails | Table & room linking emails | JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | QA all linking emails before send | Table & room linking emails | TBD | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Stage mock linking email for JG approval | Table & room linking emails | TBD | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Build run-of-show + designate transition leads | Vendors & logistics | Fernando + Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Collect tech stand requirements + send to client | Vendors & logistics | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Design signage + badges | Vendors & logistics | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | JG sends design requests to Fernando + Christina | Vendors & logistics | JG | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Marketing materials for Informa submission | Vendors & logistics | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 2 | Vendor invoice tracking + payment | Vendors & logistics | Christina | none | Claude drafts the content / first pass; a named human reviews and approves in one click before it ships.
Tier 3 | 858 House check-in + table reservations setup | Activation operations | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | 858 House venue + lounge setup coordination | Activation operations | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Brief chief of staff | Activation operations | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Client completes GRIP operator preference selections (top 40) | Activation operations | Client partner | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Confirm + sign guest speaker agreement | Activation operations | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Confirm GRIP designate per partner | Activation operations | Client partner | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Coordinate speaker travel + hotel invoice reimbursement | Activation operations | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Day-of check-in setup + live no-show tracking | Activation operations | On-site team | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | GRIP on-site support + ESM coverage | Activation operations | Client partner + ESMs | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Guest speaker briefing meeting | Activation operations | Fernando + Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Hold moderator prep meeting + distribute notes | Activation operations | JG | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Outreach to guest speaker candidates | Activation operations | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Prep workshop room supplies + Granola setup | Activation operations | Fernando + Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Presentation: AV rehearsal + final speaker prep | Activation operations | JG + Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Recruit + confirm workshop moderators | Activation operations | Fernando + JG | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Client deal strategy call | Client comms & calls | JG | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Client debrief call | Client comms & calls | Client partner | ongoing | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Client prep kickoff call | Client comms & calls | Client partner + Nic | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Collect client to-dos | Client comms & calls | Client partner | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Connect ESM with client (intro) | Client comms & calls | Client partner | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | ESM introductions, tracking on-site | Client comms & calls | Client partner + ESMs | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | ESM tracks top target intros with clients | Client comms & calls | Client partner + ESMs | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Post-event client thank you message via text or LinkedIn | Client comms & calls | JG | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Run prioritization exercise with clients | Client dossiers | Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | On-site team picks up handwritten notes package | Handwritten notes | On-site team | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Package + ship handwritten notes to venue/hotel | Handwritten notes | Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Place handwritten notes on seats/tables | Handwritten notes | On-site team | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Produce handwritten notes (run machine) | Handwritten notes | Christina | ongoing | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | QA handwritten notes + envelopes | Handwritten notes | Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Write handwritten notes for on-site new additions | Handwritten notes | Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Arrange ground transportation + car rental | On-site team logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Book hotels for on-site team | On-site team logistics | Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Book team dinner reservations | On-site team logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Book team flights | On-site team logistics | Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Coordinate on-site shipping + last-minute supply run | On-site team logistics | Fernando + Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Approve Robin invoice + notify Fern for payment | Photography | Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Negotiate + sign photography contract | Photography | Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Pay photographer final invoice | Photography | Fernando + Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Pay photography deposit | Photography | Fernando + Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Robin organizes photos by operator + delivers folders | Photography | Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Event internal kick-off call | Project setup & cadence | Fernando + Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Fern → Christina handoff | Project setup & cadence | Fernando + Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Internal post-event debrief | Project setup & cadence | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Assign seating assignments during event rehearsal | Seating & room assignments | Fernando + JG | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Input check-in data into seating automation tool (onsite) | Seating & room assignments | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Review draft assignments with clients | Seating & room assignments | JG | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Confirm AV + tech setup | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Confirm Wi-Fi + internet access | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Confirm floor plan + capacity from venue/Informa | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Designate music lead + build playlists | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Food + beverage + espresso cart coordination | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Furniture rental order | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Hire extra staff | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Menu preapproval in writing | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | On-site team picks up marketing collateral | Vendors & logistics | On-site team | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Order + ship marketing collateral | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Shipping logistics | Vendors & logistics | Fernando + Christina | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Swag order | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Vendor parking + load-in/load-out coordination | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.
Tier 3 | Venue walkthrough + event rehearsal | Vendors & logistics | Fernando | none | Human-led — relationship, physical, live, financial, or external-client work. Agent only supports with prep, reminders, and briefs.

## Tier legend
858 task automation tiers
Tier | What it means | Human involvement | Tasks | % of library
Tier 1 | Fully automatable. An agent runs after a trigger (event created, registration change, picks finished, time-based) and completes the task end-to-end. | None after the trigger | 51 | 31.29%
Tier 2 | Claude drafts; a human approves. Claude produces the content/first pass, a person reviews and approves with one click. | One-click review | 52 | 31.9%
Tier 3 | Human-required. Relationship, physical, live, or judgment work the agent can only support (prep, reminders, briefs). | Human does the work | 60 | 36.81%
Total |  |  | 163 | 100%
Note: | Tiers are a first-pass classification based on each task's nature. Tier 2 tasks are the migration path — once a draft-and-approve pattern proves reliable, it graduates to Tier 1. Adjust any row directly in the 'Task library' tab.